## Sheet1
Its That Easy Budget And Time Line
Module | Work Description | Time Line(Man Days)(Include Coding/Testing and Deployment) | Milestone
UI Design | Home Page | 5 | M1
UI Design | UI Design Content Pages | 2 | M1
UI Design | Work Flow(e.g Forms For Clients) | 3 | M1
Admin Panel Customer Support | User's Management | 1 | M1
Admin Panel Customer Support | Site Content Pages Management | 1 | M1
Admin Panel Customer Support | Lawyer's Management(Adding/ Updating lawyers) | 2 | M1
Admin Panel Customer Support | View / Update Calendar Bookings | 3 | M2
Admin Panel Customer Support | Payment Management(e.g. Check Status, Initiate refunds) | 2 | M2
Admin Panel Customer Support | Client's Query Or Support Ticket Management | 3 | M3
Admin Panel Customer Support | Promotional Email Schedule And Management | 5 | M3
Lawyer's Portal | View Bookings | 1 | M2
Lawyer's Portal | Update Profile | 1 | M2
Lawyer's Portal | Update Calendar(e.g. Make dates /Slots Unavailable or Vice Versa) | 2 | M3
Client's Portal | Registration / Login | 1 | M1
Client's Portal | Booking Slots For Lawyers | 5 | M2
Client's Portal | Payment for booking | 3 | M2
Client's Portal | View Bookings | 1 | M2
Client's Portal | Check Payments(Include Cancellation Of Booking and Refund ) | 2 | M3
Client's Portal | Contact Support | 3 | M3
Client's Portal
Front Web | Home Pages | 3 | M1
Front Web | Content Pages | 3 | M1
Total Man Days = 52
Total Cost Budget = Rs.75000